{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["2026入库项目统计表","优先实施项目表"],"not_rendered":{"defined_names":4},"read":"whole","date_system":"1900"}

{"sheet":"2026入库项目统计表","index":0,"n_rows":80,"n_cols":17,"rows_kept":80,"merged":[[0,0,0,1],[1,0,1,16],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,3,8],[2,9,3,9],[2,10,3,10],[2,11,2,12],[2,13,3,13],[2,14,3,14],[2,15,3,15],[2,16,3,16]]}
["附件2"]
["双阳区2026年度财政衔接推进乡村振兴补助资金入库项目表"]
["序号","市县","项目类型","项目名称","建设性质","实施地点","时间进度",null,"责任单位","建设内容与规模","项目预算总投资\n（万元）","其中",null,"受益对象","绩效目标","联农带农机制","备注"]
[{"$nulls":6},"计划开工时间","计划完工时间",{"$nulls":3},"财政衔接资金\n（万元）","其他资金（万元）"]
[1,"双阳区","产业项目","蔡家村梅花鹿良种繁育项目","新建","原鼎庆燃气院内","2026.6","2026.10","鹿乡镇","新建鹿圈3000平方米，购买纯种梅花鹿60只",400,400,null,"脱贫户29户分红及周边打工村民","1.在蔡家村新建鹿圈3000平方米购买梅花鹿60只。2.增加村集体收益及脱贫户分红促进乡村振兴。增加村集体收益及脱贫户分红","带动脱贫户分红及周边村民打工收入"]
[2,"双阳区","产业项目","尖山村梅花鹿养殖扩建项目","扩建","尖山村4社","2026.4","2026.6","鹿乡镇","购买梅花鹿50头",100,100,null,"受益496户1249人，其中脱贫户15户27人监测对象2户3人","1.在尖山村新购买梅花鹿50只。2.增加村集体收益及脱贫户分红促进乡村振兴。增加村集体收益及脱贫户分红","合作社引领带动农户"]
[3,"双阳区","产业项目","方家村梅花鹿养殖项目","新建","方家村小学","2026.6","2026.10","鹿乡镇","新建鹿圈4000平方米，购买梅花鹿50只",100,100,null,"脱贫户23户分红及周边打工村民","1.在方家村新建鹿圈4000平方米购买梅花鹿50只。2.增加村集体收益及脱贫户分红促进乡村振兴。增加村集体收益及脱贫户分红","带动脱贫户分红及周边村民打工收入"]
[4,"双阳区","产业项目","石灰村梅花鹿养殖项目","新建","石灰富鸿公司","2025年8月","2025年11月","鹿乡镇","新建鹿舍3000平方米，购买梅花鹿80只",200,200,null,"受益75户，期中脱贫户3户6人","1.在石灰村新建鹿圈3000平方米购买梅花鹿80只。2.增加村集体收益及脱贫户分红促进乡村振兴。增加村集体收益及脱贫户分红","村集体引领带动农户"]
[5,"双阳区","基础设施","鹿乡村11社盖板桥建设项目","新建","鹿乡村","2026-05-01","2026-08-01","鹿乡镇","新建6*8盖板桥一座","35",35,null,"全体村民","1.在鹿乡村十一社修建6*8盖板桥一座。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","受益群众2000人"]
[6,"双阳区","基础设施","常家村3社水泥路建设项目","新建","常家村3.4.5.9.11社","2026-06-01","2026-10-01","鹿乡镇","新修水泥路长1.36千米、宽4米，新建6*8米盖板桥1座",120,120,null,"受益农户660人","1.在常家村三社等修建水泥路1360米、6*8盖板桥一座。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","吸纳脱贫人口务工，增加贫困人口收入。"]
[7,"双阳区","基础设施","镇区村东街屯水泥路建设项目","新建","镇区村东街屯","2026-06-01","2026-10-01","鹿乡镇","新建水泥路4米宽1450长米",100,100,null,"镇区村东街屯89户267人脱贫困户6人","1.在镇区村东街屯修建水泥路1450米。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","带动3人劳动就业"]
[8,"双阳区","基础设施","尖山村3社盖板桥建设项目","新建","尖山村3社","2026-05-01","2026-10-01","鹿乡镇","6*8米盖板桥1座。",35,35,null,"受益农户28户87人其中脱贫户2户3人","1.在尖山村三社修建6*8盖板桥一座。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","村集体引领带农"]
[9,"双阳区","基础设施","杏树村盖板桥建设项目","新建","杏树河支流，9社和10社之间","2026-05-01","2026-10-01","鹿乡镇","6*8米盖板桥1座",30,30,null,"受益60户195人，其中脱贫户3户3人。","1.在杏树村九社修建6*8盖板桥一座。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","村集体引领带动农户"]
[10,"双阳区","基础设施","丁家村4社沥青路建设项目","新建","丁家4社","2026-05-01","2026-10-01","鹿乡镇","新建水泥路改沥青路2064.9m",127,127,null,"受益72户，210人，其中脱贫户9户11人","1.在丁家村四社修建道路2064.9米。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","村集体引领带动农户"]
[11,"双阳区","基础设施","石溪村六社盖板桥建设项目","新建","石溪村六社","2026-05-01","2026-10-01","鹿乡镇","新修6*8盖板桥一座",30,30,null,"受益30户92人，其中脱贫户5户10人，监测对象0户0人。","1.在石溪村六社修建6*8盖板桥一座。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","吸纳脱贫人口3人务工，年人均增收500元"]
[12,"双阳区","基础设施","鹿乡村1社盖板桥建设项目","新建","鹿乡村1社","2026-06-01","2026-10-01","鹿乡镇","新建6*12米盖板桥1座",60,60,null,"1社村民","1.在鹿乡村一社修建6*12盖板桥一座。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","受益群众260人"]
[13,"双阳区","基础设施","刘家村九社盖板桥建设项目","新建","刘家村九社","2026-05-01","2026-10-01","鹿乡镇","新建4*6盖板桥一座",25,25,null,"受益群众1000人，其中脱贫户21户28人","1.在刘家村九社修建4*6盖板桥一座。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","带动3人就业"]
[14,"双阳区","基础设施","崔家村桥涵建设项目","新建","崔家村5社","2026-05-01","2026-10-01","鹿乡镇","新建4×6米盖板桥一座",25,25,null,"受益25户82人，脱贫人口1户1人","1.在崔家村五社修建4*6盖板桥一座。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","吸纳贫困户1人务工，增加贫困人口收入"]
[15,"双阳区","基础设施","石灰村盖板桥建设项目","新建","石灰1社","2025年8月","2025年9月","鹿乡镇","6*8米盖板桥1座",30,30,null,"受益75户，期中脱贫户3户6人","1.在石灰村一社修建6*8盖板桥一座。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","村集体引领带动农户"]
[16,"双阳区","基础设施","石灰村水泥路建设项目","新建","石灰1社5社6社\n11社12社","2025年8月","2025年11月","鹿乡镇","1.2公里",72,72,null,"受益75户，期中脱贫户3户7人","1.在石灰村修建水泥路1200米。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","村集体引领带动农户"]
[17,"双阳区","基础设施","山咀村二社路边沟建设项目","新建","山咀村二社","2026年4月","2026年11月","奢岭\n街道","修建路边沟1200米",72,72,null,"受益脱贫户13户20人","1.修建屯内边沟1200米。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口2人就业。\n2.带动普通劳动力就近就业。"]
[18,"双阳区","基础设施","大屯村七社水泥路建设项目","新建","大屯村七社","2026年4月","2026年11月","奢岭\n街道","修建水泥路\n700米",50,50,null,"受益脱贫户8户17人","1.修建屯内水泥路200米。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口2人就业。\n2.带动普通劳动力就近就业。"]
[19,"双阳区","基础设施","马场村二级水源保护区排水沟建设项目","新建","马场村一社","2026年4月","2026年11月","奢岭\n街道","2级水源保护区内，修建宽5米，高1.5米，长度为600米的排水沟",80,80,null,"受益脱贫户16户26人","1.修建排水沟600米。2.改善脱贫人口及农户生态环境，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口2人就业。\n2.带动普通劳动力就近就业。"]
[20,"双阳区","基础设施","东营村二社路边沟建设项目","新建","东营村二社","2026年4月","2026年11月","奢岭\n街道","修建路边沟2500米",150,150,null,"受益脱贫户11户29人","1.修建屯内边沟2500米。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口2人就业。\n2.带动普通劳动力就近就业。"]
[21,"双阳区","基础设施","平湖街道小龙村水泥路建设项目","新建","小龙村1社","2026-05-01","2026-10-01","平湖街道","新建水泥路1200米，盖板涵1个。",107,107,null,"受益脱贫户4户10人。","1.在小龙村1社修建新水泥路1200米，盖板涵1个。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口4人务工，提高收入。2.带动普通劳动力就近就业。"]
[22,"双阳区","基础设施","平湖街道双桥村南岗泡子生态环境治理建设项目","新建","双桥村村朝阳社","2026-05-01","2026-10-01","平湖街道","南岗泡子周边建围栏565m、水面清淤13000㎡，石头护坡。",100,100,null,"受益脱贫户6户13人","1.在南岗泡子建周边围栏565m、水面清淤13000㎡、护砌500m。2.解决脱贫人口及农户生态环境，改善农村居住环境和生产生活条件，促进乡村振兴.","1.带动脱贫人口3人务工，提高收入。2.带动普通劳动力就近就业。"]
[23,"双阳区","基础设施","平湖街道林家村水泥路建设项目","新建","林家村10社","2026-05-01","2026-10-01","平湖街道","新建水泥路1.8公里。",108,108,null,"受益脱贫31户89人。","1.在林家村十社新建1.8公里水泥路。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口2人务工，提高收入。2.带动普通劳动力就近就业。"]
[24,"双阳区","基础设施","平湖街道黑鱼村8社路边沟建设项目","新建","黑鱼村8社","2026-05-01","2026-10-01","平湖街道","新建路边沟1100延长米。",57,57,null,"受益脱贫户17户29人。","1.在黑鱼村8社修建新建路边沟1100延长米。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口3人务工，提高收入。2.带动普通劳动力就近就业。"]
[25,"双阳区","基础设施","平湖街道双湾村边沟建设项目","新建","平湖街道双湾村4社","2026-05-01","2026-10-01","平湖街道","新建边沟900米。",54,54,null,"受益脱贫户5户11人","1.在双湾村四社修建边沟900米。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","1.带动脱贫人口3人务工，提高收入。2.带动普通劳动力就近就业。"]
[26,"双阳区","基础设施","平湖街道杨家三社、七社边沟项目","新建","杨家三社、七社边沟","2026-09-01","2026-12-01","平湖街道","新建石砌边沟约600米",58,58,null,"受益脱贫户5户12人","1.在杨家三社、七社修建石砌边沟600延米。2.解决脱贫\n户及农户排水问题","吸纳脱贫户2人务工，年增收3000.00元。"]
[27,"双阳区","基础设施","平湖街道宋家村水泥路建设项目","新建","宋家村1/3/4/5/6/7/8/10","2026.5.1","2026.10.31","平湖街道","新建水泥路1080米",58,58,null,"收益脱贫户15户，21人。","1.在宋家村内新建1.08公里水泥路。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口2人务工，提高收入。2.带动普通劳动力就近就业。"]
[28,"双阳区","产业项目","平湖街道尚家村红菇娘果汁生产加工销售项目","新建","尚家村2社","2026.5.1","2026.11.31","平湖街道","新建生产车间800平，储存冷藏保鲜库400平，购置生产加工设备1套。",420,420,null,"收益脱贫户23户，45人。","1.在尚家村2社新建红菇娘加工生产车间及冷藏保鲜库，购置生产加工设备1套。2.该项目建成后壮大村集体经济收入，增加脱贫人口收入。","1.带动脱贫人口4人以上务工。2.建成后带动尚家村周边普通劳动力就近就业。"]
[29,"双阳区","产业项目","平湖街道尚家村冷藏保鲜库建设项目","新建","尚家村2社","2026-05-01","2026-10-01","平湖街道","新建冷藏保鲜库1200㎡，占地面积3000平。",300,300,null,"受益脱贫户23户45人","1.在尚家村2社新建冷藏保鲜库1200㎡。2.解决农户及脱贫人口蔬菜储存问题；3.壮大村集体经济","1.带动脱贫人口15人务工，提高收入。2.带动普通劳动力就近就业。"]
[30,"双阳区","产业项目","平湖街道杨家村水稻加工项目","新建","杨家村12社","2025-09-01","2025-12-01","平湖街道","新建厂房1000平方米；水稻烘干塔一座；水稻加工设备一套；地量衡一个；200KW变压器2个；硬化地面3000平方米，管理房一个。",350,350,null,"受益脱贫户17户50人。","1.在杨家村12社新建厂房1000平；水稻烘干塔一座；水稻加工设备一套；地量衡一个；200KW变压器2个；硬化地面3000平方米。2.解决农户水稻加工问题；3.壮大村集体经济，促进乡村产业发展。","1.带动脱贫人口5人务工，提高收入。2.带动本村普通劳动力就近就业。"]
[31,"双阳区","产业项目","平湖街道梨树村纯粮酒酿造加工项目","新建","平湖街道梨树村6社","2026.5.1","2026.10.31","平湖街道","新建梨树村纯粮酒加工，新建酒窖及厂房、库房，总面积约500平以及酿酒设备设施，总投资380万元。",380,380,null,"受益脱贫7户15人","1.在梨树村新建酒窖及厂房、库房，总面积约500平以及酿酒设备设施。2.增加脱贫人口收入。3.壮大村集体经济收入。","1带动脱贫人口3人务工，提高收入。2带动普通劳动力就近就业。"]
[32,"双阳区","产业项目","平湖街道城郊村冷藏库建设项目","新建","城郊村村部院内","2026.5.1","2026.10.31","平湖街道","改建冷藏库，面积约250平方",55,55,null,"城郊村脱贫户","1.在城郊村村部改建冷藏库250平。2.壮大村集体经济收入。","1带动脱贫人口2人务工，提高收入。2带动普通劳动力就近就业。"]
[33,"双阳区","产业项目","平湖街道宋家村库房扩建及设施完善项目","新建","宋家村2社","2026.5.1","2026.10.31","平湖街道","扩建仓储库房约130平方，新建管理房约80平方。",58,58,null,"收益脱贫户25户35人。","1.在宋家村扩建库房130平，新建管理房80平。2.增加脱贫人口收入。3.壮大村集体经济收入。","1带动脱贫人口2人务工，提高收入。2带动普通劳动力就近就业。"]
[34,"双阳区","基础设施","于家村一社水泥路建设项目","新建","云山街道于家村一社","2026-05-01","2026-10-01","云山街道","新建水泥路1.3km",60,60,null,"受益脱贫户34户52人。","1.在于家村一社新建1.3公里水泥路。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口2人务工，提高收入。2.带动普通劳动力就近就业。"]
[35,"双阳区","基础设施","于家村二社水泥路建设项目","新建","云山街道于家村二社","2026-05-01","2026-10-01","云山街道","新建水泥路2km",90,90,null,"受益脱贫户34户52人。","1.在于家村二社新建2公里水泥路。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口6人务工，提高收入。2.带动普通劳动力就近就业。"]
[36,"双阳区","基础设施","于家村三社水泥路建设项目","新建","云山街道于家村三社","2026-05-01","2026-10-01","云山街道","新建水泥路1.5km",140,140,null,"受益脱贫户34户52人。","1.在于家村三社新建1.5公里水泥路。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口6人务工，提高收入。2.带动普通劳动力就近就业。"]
[37,"双阳区","产业项目","太平镇土门村土豆粉坊项目","新建","土门村6社","2026-05-01","2026-09-01","太平镇","利用土门村原村部房屋（现以闲置）及闲置操场、仓房作为粉坊原材料处理、加工、包装场地，发展壮大村集体经济，计划投资150万元。其中80万元用于相关设备的采购，60万元用于原材料的采购，10万元用于成品的运输及产品铺设、设备后续维护等。预计年增收20万元。",150,150,null,"受益210户438人，其中脱贫户12户25人，监测对象1户2人。","改建厂房420平米，购买土豆粉生产设备8台。","因土豆粉的原材料为土豆，因此通过建设土豆粉坊来号召一部分村民种植土豆，村集体负责回收村民种植的成品土豆，不仅可以降低生产成本，还在提高村集体经济的同时带动村民经济发展。"]
[38,"双阳区","产业项目","太平镇长山村梅花鹿养殖项目","新建","长山村11社","2026-05-02","2026-09-02","太平镇","利用长山村原有圈舍场地（现以闲置）仓房、村集体水田地40亩、旱田地20亩作为基础，扩建维修养殖梅花鹿、发展壮大村集体经济，计划投资100万元。其中80万用于购买梅花鹿，20万用于基础设施维修、扩建。预计年增收8万元。",100,100,null,"受益670户3200人，其中脱贫户48户112人。","改建原圈舍2500平米，新建存储库一个，购买粉料机一台，购买梅花鹿80头，","该项目吸纳贫困户6人务工，年增加收入6000元"]
[39,"双阳区","产业项目","一面山村梅花鹿养殖配套设施建设项目","新建","一面山村1社南山","2026-05-20","2026-10-01","太平镇","村集体经济扩大养殖规模，修建鹿舍一栋，隔离圈舍1栋、存料大库382平米、青储库一个、挡墙一面、外围扩网散养10000平米。",110,110,null,"受益195户382人，其中脱贫户13户34人。","新建外围扩网圈舍10000平米，新建382平米存储库个，青储库一个。","该项目吸纳贫困户2人务工，年增加收入3000元"]
[40,"双阳区","产业项目","太平镇小石村玉米食品加工及配套设施项目","新建","小石村1社","2026-05-01","2026-09-01","太平镇","利用原有鲜食玉米厂房新增加玉米面条、发糕、窝头生产设备及鲜食玉米缓化设备。同时建设冷库30平方米。",150,150,null,"受益450户1800人，其中脱贫户40户60人，监测对象1户2人。","建设冷库30平米，购买鲜食玉米缓化设备一台，改造提升原有厂房配备。","该项目吸纳贫困户2人务工，年增加收入3000元"]
[41,"双阳区","产业项目","肚带河村山水泉水稻种植加工项目","新建","肚带河村4社","2026-05-01","2026-09-01","太平镇","利用翔鹿山庄原有建设用地，建设240平米粮米加工厂一座，升级稻米加工机械，购买水稻育秧、插秧、收割机械等。",200,200,null,"受益120户400人，其中脱贫户20户43人，监测对象2户4人。","通过水稻播种、秋收、稻米加工等一条龙服务，实现农户增产增收。","该项目吸纳贫困户2人务工，年增加收入3000元"]
[42,"双阳区","基础设施","桦木村2、4社盖板桥建设项目","新建","桦木村2、4社","2026-05-01","2026-08-01","太平镇","2社新建12*4米盖板桥一座，4社新建8*6米，盖板桥一座，桥边护砌40米",42,42,null,"受益240户744人，其中脱贫户10户13人，监测户0户0人。","1、新建12*4米、8*6米，盖板桥两座，桥边护砌40延长米。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","该项目吸纳贫困户2人务工，年增加收入3000元"]
[43,"双阳区","基础设施","太平镇太平村7社盖板桥建设项目","新建","太平村7社","2026-05-01","2026-08-01","太平镇","新建盖板桥1座，规格8*6米。护砌35米",35,35,null,"受益70户210人，其中脱贫户7户8人.","1、新建8*6米盖板桥一座，桥边护砌35延长米。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","该项目吸纳贫困户2人务工，年增加收入2000元"]
[44,"双阳区","基础设施","太平镇太阳村7、8社盖板桥及砂石路建设项目","新建","太平镇太阳村7、8社","2026-05-01","2026-08-01","太平镇","新建盖板桥3座，其中2座5*6规格，1座5*10规格，砂石路1600米。",59,59,null,"受益82户236人，其中脱贫户9户24人，监测户0户0人。","维修盖板桥3座，其中2座5*6规格，1座5*10规格，砂石路1600米，解决农民拉地难问题同时解决水毁道路","该项目吸纳贫困户1人务工，年增加收入2000元"]
[45,"双阳区","基础设施","太平镇土门村3社边沟建设项目","新建","土门村3社","2026-05-01","2026-08-01","太平镇","新建石砌边沟600延长米，入户盖板14个",45,45,null,"受益26户65人，其中脱贫2户3人。","1、新建石砌边沟600延长米，入户盖板14个。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","该项目吸纳贫困户4人务工，年增加收入4000元"]
[46,"双阳区","基础设施","太平镇小河村3社盖板桥建设项目","新建","太平镇小河村3社","2026-05-01","2026-08-01","太平镇","新建盖板桥1座，规格8*6米",35,35,null,"受益50户115人，其中脱贫户3户8人.","1、新建8*6米盖板桥一座。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","该项目吸纳贫困户1人务工，年增加收入1000元"]
[47,"双阳区","基础设施","太平镇长山村5社盖板桥建设项目","新建","太平镇长山村5社","2026-04-01","2026-09-01","太平镇","新建盖板桥一座，规格8*6米，护砌30米",30,30,null,"受益135户720人，其中脱贫户7户7人.","1、新建8*6米盖板桥一座，护砌30延长米。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","该项目吸纳贫困户4人务工，年增加收入4000元"]
[48,"双阳区","基础设施","太平镇治国村后荒营屯边沟建设项目","新建","太平镇治国村后荒营屯","2026-05-01","2026-08-01","太平镇","新建石砌边1000余延米，入户盖板桥25个",60,60,null,"受益78户223人，其中脱贫户4户7人.","1、新建石砌边沟1000延长米，入户盖板25个。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","该项目吸纳贫困户2人务工，年增加收入3000元"]
[49,"双阳区","基础设施","太平镇长炮村六社石砌边沟建设项目","新建","长炮村6社","2026-05-20","2026-09-01","太平镇","新建石砌边沟1480米，入户盖板44个",59,59,null,"受益66户347人，其中脱贫户7户19人。","1、新建石砌边沟1480延长米，入户盖板44个。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","该项目吸纳贫困户2人务工，年增加收入3000元"]
[50,"双阳区","基础设施","太平镇田家村3、8社石砌边沟建设项目","新建","田家村3、8社","2026-05-01","2026-08-01","太平镇","新建石砌边沟3000延米、入户盖板桥15个",150,150,null,"受益人口105户，其中脱贫户8户12人","1、新建石砌边沟3000延长米，入户盖板15个。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","该项目吸纳贫困户4人务工，年增加收入4000元"]
[51,"双阳区","基础设施","太平镇齐瓦房村5社盖板桥建设项目","新建","齐瓦房村5社","2026-05-01","2026-08-01","太平镇","新建盖板桥1座，规格8*6米。",28,28,null,"受益人口23户，其中脱贫户1户3人","1、新建8*6米盖板桥一座。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","该项目吸纳贫困户2人务工，年增加收入2000元"]
[52,"双阳区","产业项目","齐家镇绿色蔬菜产业园建设项目二期","新建","齐家镇双阳良种繁育场","2026-05-01","2026-08-01","齐家镇","新建20米宽双拱双模日光温室7座",700,700,null,"受益2200户6000人，其中脱贫户50户60人，监测对象3户5人。","1、预计年产蔬菜300吨，2、预计年收益30万元以上。","吸纳脱贫户10人务工，增加贫困人口年人均增收2000元。"]
[53,"双阳区","产业项目","齐家镇官地村果园建设项目","新建","官地村前官地屯","2026-05-01","2026-08-01","齐家镇","新建20米宽双拱双模日光温室3座",300,300,null,"受益143户301人，其中脱贫户16户27人，监测对象10户20人。","1、预计年产水果20吨，2、预计年收益20万元以上。","吸纳脱贫户5人务工，增加贫困人口年人均增收2000元。"]
[54,"双阳区","基础设施","管家村4、5、6、10社水泥路建设项目","新建","管家村4、5、6、10社","2026-05-01","2026-08-01","齐家镇","新建宽度4.5米的水泥路4公里",220,220,null,"收益256户765人，其中脱贫户9户19人，监测户1户2人。","该屯紧邻红旗河、双阳河，属于低洼易涝地段，雨季时路面损毁严重，村民反映强烈，修复后解决村民出行难问题。","若工程性质允许本地村民参与，预计人均增收1000元。"]
[55,"双阳区","基础设施","永安村3、4社水泥路建设项目","新建","永安村3、4社","2026-05-01","2026-08-01","齐家镇","新建4米宽水泥路3.5公里。",175,175,null,"受益130户450人其中脱贫户7户13人监测户1户2人。","修建水泥路3.5公里，有效解决百姓出行难。","吸纳脱贫户5人务工，增加贫困人口年人均增收2000元。"]
[56,"双阳区","基础设施","下河村下磨石沟屯，3、11社水泥路建设项目","新建","下河村下磨石沟屯、三社、十一社","2026-05-01","2026-08-01","齐家镇","新建4米宽水泥路下磨石沟屯1公里、三社0.9公里、十一社新建水泥路0.6公里，共计2.5公里",125,125,null,"受益下河村下磨石沟、三社、十一社全体村民143户712人。","修建水泥路2.5公里，有效解决百姓出行难。","吸纳脱贫户16人务工，增加贫困人口年人均增收2000元。"]
[57,"双阳区","基础设施","长兴村5、7社边沟建设项目","新建","长兴村5、7社","2026-05-01","2026-08-01","齐家镇","新建边沟1731.3米，入户盖板40处。",98,98,null,"受益521户 1109人，其中脱贫户7户12人，监测户3户5人。","修建边沟1730余米，解决农户内涝排水问题。","吸纳脱贫户5人务工，增加贫困人口年人均增收2000元。"]
[58,"双阳区","产业项目","庄家村煎饼生产加工厂项目","新建","庄家村","2026-05-01","2026-10-01","山河街道","生产厂房面积约1000平10万级食品净化车间，库房面积约500平主要设备：1.全自动煎饼机20台；2.水磨机2台；3.恒温发酵罐4个；4.蒸饭机3台；5.自动化叠煎饼机2台；6.包装机1台；7.封口机3台，运营模式：村集体+企业+农户入股方式，完成年生产东北软煎饼50万斤。",300,200,100,"全村受益210户650人，其中脱贫户15户40人，监测对象6户20人。","1.预计村集体经济收入增加60万元；2.将会带动本村农户就业50人。","吸纳脱贫户8人务工，增加脱贫人口年人均增收1000元。"]
[59,"双阳区","产业项目","三家村粮米加工厂项目","新建","三家村","2026-05-01","2026-10-01","山河街道","生产厂房面积约500平，储粮仓库面积约300平1.筛选清理设备(溜筛，振动筛，高速除稗筛等)；2.比重去石机；3.磁选设备(磁栏，永磁滚筒等)；4.砻谷机；5.碾米机；6.米筛(白米溜筛，平面回转筛等)；7.包装设备；8.辅助设备(斗式提升机等)；9.大米色选机；10.除尘器。",260,150,110,"受益320户760人，其中脱贫户10户20人，监测对象4户8人。","1.预计村集体经济收入增加20万元；2.将会带动本村农户就业80人。","吸纳脱贫户3人务工，增加脱贫人口年人均增收500元。"]
[60,"双阳区","产业项目","烧锅村粮食收储加工项目","新建","烧锅村","2026-05-01","2026-10-01","山河街道","134米长，40米宽罩棚仓一栋",250,200,50,"村集体和企业","1.年收益增加10余万元；2.增加粮食储存能力26000吨。","增加服务合作社和家庭农场50余个。增加用工20余人。"]
[61,"双阳区","产业项目","吉林省宝善村鹿业养殖有限公司扩建项目","扩建","宝善村","2026-05-01","2026-10-01","山河街道","预计购买生产公梅花鹿200头，种公40头，毛桃公200头，二母鹿200头。",500,200,300,"发展壮大村集体经济","1.增加村民收入；2.吸纳脱贫户2人务工。","吸纳脱贫户2人务工，增加贫困人口年人均增收500元。"]
[62,"双阳区","产业项目","吉林省泽越农业有限公司玉米加工建设项目","新建","隆兴村","2026-05-01","2026-10-01","山河街道","租赁场地、租赁土地、购买玉米加工设备（玉米面机械、玉米条机械）",350,150,200,"发展壮大村集体经济","1.增加村集体收入；2.带动脱贫人口务工10人。","吸纳脱贫户10人务工，增加贫困人口年人均增收500元。"]
[63,"双阳区","基础设施","沿河村2、5、6社水泥路建设项目","新建","沿河村2、5、6社","2026-05-01","2026-10-01","山河街道","修建沿河村2、5、6社水泥路，全长2公里，宽4米。",130,130,null,"受益96户378人，脱贫户共5户9人，监测户1户2人。","1.修建沿河村2、5、6社水泥路，全长2公里，宽4米；2.解决378人出行难问题。","吸纳脱贫户1人务工，增加脱贫人口年人均增收500元。"]
[64,"双阳区","基础设施","五家村10社水泥路建设项目","新建","五家村10社","2026-05-01","2026-10-01","山河街道","三条支路，一条干路，一条巷路，长2.6公里*4米。",150,150,null,"受益31户128人。","1.修建长2.6公里*4米水泥路；2.解决农户112人出行难的问题。","吸纳脱贫户2人务工，增加贫困人口年人均增收500元。"]
[65,"双阳区","基础设施","阳平村4社路边沟建设项目","新建","阳平村4社","2026-05-01","2026-10-01","山河街道","全长1公里，双侧边沟。",59,59,null,"受益50户110人。","1.修建长1公里，双侧边沟；2.解决农户110人排水问题。","吸纳脱贫户2人务工，增加贫困人口年人均增收500元。"]
[66,"双阳区","基础设施","双营乡黄金村\n路边沟建设项目","新建","黄金村","2026-05-01","2026-10-01","双营乡","新建石砌路边沟5000米",225,225,null,"受益脱贫户29户52人","1.在黄金村新建5000米路边沟。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口3人务工，提高收入。2.带动普通劳动力就近就业。"]
[67,"双阳区","基础设施","双营乡庞家村\n路边沟建设项目","新建","庞家村1社、2社、3社、7社、8社、9社、10社、12社","2026-05-01","2026-10-01","双营乡","新建石砌路边沟6000米",280,280,null,"受益脱贫户14户28人","1.在庞家村1、2、3、7、8、9、10、12社新建6000米路边沟。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口4人务工，提高收入。2.带动普通劳动力就近就业。"]
[68,"双阳区","基础设施","双营乡大营村大康屯路边沟建设项目","新建","大营村6社、7社、8社","2026-05-01","2026-10-01","双营乡","新建石砌路边沟\n1200米",96,96,null,"受益脱贫户34户64人","1.在大营村6、7、8社新建1200米路边沟。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口2人务工，提高收入。2.带动普通劳动力就近就业。"]
[69,"双阳区","基础设施","双营乡黄金村\n道路白改黑建设项目","新建","黄金村1社、2社、3社、4社、5社、6社","2026-05-01","2026-10-01","双营乡","道路白改黑6000米",270,270,null,"受益脱贫户29户52人","1.在黄金村1、2、3、4、5、6社新建6000白改黑道路。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口3人务工，提高收入。2.带动普通劳动力就近就业。"]
[70,"双阳区","基础设施","双营乡庞家村5、10社盖板桥建设项目","新建","庞家村5社、10社","2026-05-01","2026-10-01","双营乡","5社新建4米*6米\n盖板桥1座；10社新建6米*8米盖板桥1座。",57,57,null,"受益脱贫户14户28人","1.在庞家村5、10社新建盖板桥2座。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","1.带动脱贫人口2人务工，提高收入。2.带动普通劳动力就近就业。"]
[71,"双阳区","其它类","庭院经济补助资金项目","新建","各村","2025-01-01","2025-12-01","各乡镇（街道）","鼓励脱贫户发展小种植、小养殖、小加工等庭院经济，发展户数1800户以上，发展面积达到2500亩，分批次发放奖补资金。",280,280,null,"受益脱贫户2000户4000人。","1.发展户数2000户；2.面积100万平方米。3.预计发放奖补资金280万元。","发展庭院经济，户均增收1000元以上。"]
[72,"双阳区","其它类","乡村公益岗补助资金项目","新建","各村","2025-01-01","2025-12-01","各乡镇（街道）","鼓励弱半劳动能力的脱贫人口参与村屯管理和建设，全年开发各类型乡村公益岗位1000人以上。",360,360,null,"受益脱贫人口1000人。","1.开发脱贫人口乡村公益岗位1000人。2.预计发放补助资金360万元。","开发乡村公益岗位，人均增收3000元以上。"]
[73,"双阳区","其它类","小额贴息项目","新建","各村","2025-01-01","2025-12-01","各乡镇（街道）","鼓励脱贫户通过贷款方式自主发展产业，贷款户数达到200户，贷款金额1000万元，分批次发放贴息资金。",30,30,null,"受益脱贫户200户375人。","1.贷款金额1000万元；2.预计发放贴息30万元。","落实脱贫人口小额贴息项目，人均增收1500以上。"]
[74,"双阳区","其它类","雨露计划项目","新建","各村","2025-01-01","2025-12-01","各乡镇（街道）","落实雨露计划扶贫政策，对符合条件的脱贫人口学生每年每生发放3000元。",22,22,null,"受益脱贫人口77人。","1.预计发放雨露计划补助资金22万元。","落实脱贫人口雨露计划扶持政策，人均增收3000元。"]
[75,"双阳区","其它类","脱贫人口务工交通补助项目","新建","各村","2025-01-01","2025-12-01","各乡镇（街道）","对省外务工、省内县外务工脱贫人口交通费用进行补贴。全年补贴人数200人，分批次发放奖补资金。",15,15,null,"受益脱贫人口200人。","1.预计发放务工交通补助资金10万元。","落实脱贫人口务工交通补助政策，人均增收300元。"]
["合计",{"$nulls":9},{"$f":"SUM(K5:K79)","v":10706},{"$f":"SUM(L5:L79)","v":9981},{"$f":"SUM(M5:M79)","v":760}]

{"sheet":"优先实施项目表","index":1,"n_rows":23,"n_cols":19,"rows_kept":23,"merged":[[1,0,1,18],[2,0,2,6],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,3,6],[3,7,4,7],[3,8,4,8],[3,9,4,9],[3,10,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,18,4,18]]}
["附件："]
["双阳区2026年度财政衔接推进乡村振兴补助资金第一批项目计划表"]
["填报单位：长春市双阳区农业农村局",{"$nulls":7},"2025-12-30"]
["序号","项目类型","项目名称","建设性质","实施地点","时间进度",null,"责任单位","建设内容与规模","项目预算总投资\n（万元）","其中",{"$nulls":4},"受益对象","绩效目标","联农带农机制","备注"]
[{"$nulls":5},"计划开工时间","计划完工时间",{"$nulls":3},"中央财政衔接资金\n（万元）","省级财政衔接资金\n（万元）","市级财政衔接资金（万元）","区级财政衔接资金（万元）","其他资金（万元）"]
[1,"产业项目","齐家镇绿色蔬菜产业园建设项目二期","续建","齐家镇双阳良种繁育场","2026-05-01","2026-08-01","齐家镇","新建20米宽双拱双模日光温室7座",700,350,250,100,null,null,"受益2200户6000人，其中脱贫户50户60人，监测对象3户5人。","1.预计年产蔬菜300吨，2、预计年收益30万元以上。","吸纳脱贫户10人务工，增加贫困人口年人均增收2000元。"]
[2,"产业项目","平湖街道尚家村红菇娘果汁生产加工销售项目","新建","尚家村2社","2026-05-01","2026-11-01","平湖街道","新建生产车间800平，储存冷藏保鲜库400平，购置生产加工设备1套。",420,270,150,{"$nulls":3},"受益脱贫户23户，45人。","1.新建红菇娘加工生产车间及冷藏保鲜库，购置生产加工设备1套。2.该项目建成后壮大村集体经济收入，增加脱贫人口收入。","吸纳脱贫人口4人以上务工。带动尚家村周边普通劳动力就近就业。"]
[3,"产业项目","三家村粮米加工厂项目","新建","三家村","2026-05-01","2026-10-01","山河街道","生产厂房面积约500平，储粮仓库面积约300平1.筛选清理设备(溜筛，振动筛，高速除稗筛等)；2.比重去石机；3.磁选设备(磁栏，永磁滚筒等)；4.砻谷机；5.碾米机；6.米筛(白米溜筛，平面回转筛等)；7.包装设备；8.辅助设备(斗式提升机等)；9.大米色选机；10.除尘器。",150,null,50,100,null,null,"受益320户760人，其中脱贫户10户20人，监测对象4户8人。","1.预计村集体经济收入增加20万元；2.将会带动本村农户就业80人。","吸纳脱贫户3人务工，增加脱贫人口年人均增收500元。"]
[4,"产业项目","太平镇土门村土豆粉坊项目","新建","土门村6社","2026-05-01","2026-09-01","太平镇","利用土门村原村部房屋（现以闲置）及闲置操场、仓房作为粉坊原材料处理、加工、包装场地，发展壮大村集体经济，计划投资150万元。",150,150,{"$nulls":4},"受益210户438人，其中脱贫户12户25人，监测对象1户2人。","1.改建厂房420平米，购买土豆粉生产设备8台。","吸纳脱贫人口2任务共，提高村集体经济的同时带动村民经济发展。"]
[5,"产业项目","太平镇小石村玉米食品加工及配套设施项目","新建","小石村1社","2026-05-01","2026-09-01","太平镇","利用原有鲜食玉米厂房新增加玉米面条、发糕、窝头生产设备及鲜食玉米缓化设备。同时建设冷库30平方米。",150,150,{"$nulls":4},"受益450户1800人，其中脱贫户40户60人，监测对象1户2人。","1.建设冷库30平米，购买鲜食玉米缓化设备一台，改造提升原有厂房配备。","吸纳贫困户2人务工，年增加收入3000元"]
[6,"产业项目","方家村梅花鹿养殖项目","新建","方家村小学","2026-06-01","2026-11-01","鹿乡镇","新建鹿圈4000平方米，购买梅花鹿50只。",100,null,100,{"$nulls":3},"受益脱贫户23户34人。","1.新建鹿圈4000平方米购买梅花鹿50只。2.增加村集体收益及脱贫户分红","吸纳脱贫户1人务工，带动周边村民增收。"]
[7,"基础设施","鹿乡村11社盖板桥建设项目","新建","鹿乡村","2026-05-01","2026-08-01","鹿乡镇","新建6*8盖板桥一座。",30,30,{"$nulls":4},"全体村民","1.修建6*8盖板桥一座。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","吸纳群众2人务工，人均增收2000元。"]
[8,"基础设施","镇区村东街屯水泥路建设项目","新建","镇区村东街屯","2026-06-01","2026-10-01","鹿乡镇","新建水泥路4米宽1450米。",70,70,{"$nulls":4},"受益89户267人，脱贫困户6人","1.修建水泥路1450米。2.解决脱贫人口及农户出行问题，改善农村居住环境和生产生活条件，促进经济发展。","吸纳群众3人务工，人均增收1500元"]
[9,"基础设施","山咀村二社路边沟建设项目","新建","山咀村二社","2026年4月","2026年11月","奢岭街道","修建路边沟1200米。",70,null,70,{"$nulls":3},"受益脱贫户13户20人","1.修建屯内边沟1200米。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","吸纳脱贫人口2人务工。"]
[10,"基础设施","大屯村七社水泥路建设项目","新建","大屯村七社","2026年4月","2026年11月","奢岭街道","修建水泥路450米。",30,null,30,{"$nulls":3},"受益脱贫户8户17人","1.修建屯内水泥路200米。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","吸纳脱贫人口2人就业。带动普通劳动力就近就业。"]
[11,"基础设施","平湖街道小龙村水泥路建设项目","新建","小龙村1社","2026-05-01","2026-10-01","平湖街道","新建水泥路1200米，盖板涵1个。",100,100,{"$nulls":4},"受益脱贫户4户10人。","1.修建新水泥路1200米，盖板涵1个。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","吸纳脱贫人口4人务工，2.带动普通劳动力就近就业。"]
[12,"基础设施","桦木村2、4社盖板桥建设项目","新建","桦木村2、4社","2026-05-01","2026-08-01","太平镇","2社新建12*4米盖板桥一座，4社新建8*6米，盖板桥一座，桥边护砌40米。",40,40,{"$nulls":4},"受益240户744人，其中脱贫户10户13人，监测户0户0人。","1.新建12*4米、8*6米，盖板桥两座，桥边护砌40延长米。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","吸纳贫困户2人务工，年增加收入3000元"]
[13,"基础设施","太平镇治国村后荒营屯边沟建设项目","新建","太平镇治国村后荒营屯","2026-05-01","2026-08-01","太平镇","新建石砌边1000余延米，入户盖板桥25个。",60,null,60,{"$nulls":3},"受益78户223人，其中脱贫户4户7人。","1.新建石砌边沟1000延长米，入户盖板25个。2、解决脱贫人口出行难问题及农户生态环境，改善农村居住环境，促进乡村振兴","吸纳贫困户2人务工，年增加收入3000元"]
[14,"基础设施","管家村5、6社水泥路建设项目","新建","管家村5、6社","2026-05-01","2026-08-01","齐家镇","新建宽度4.5米的水泥路1.8公里。",100,null,100,{"$nulls":3},"受益149户552人，其中脱贫户1户3人。","1.新建水泥路1.8公里。2.解决村民出行难问题。","吸纳脱贫人口2人务工，预计人均增收1000元。"]
[15,"基础设施","沿河村2、5、6社水泥路建设项目","新建","沿河村2、5、6社","2026-05-01","2026-10-01","山河街道","修建沿河村2、5、6社水泥路，全长2公里，宽4米。",100,100,{"$nulls":4},"受益96户378人，脱贫户共5户9人，监测户1户2人。","1.修建沿河村2、5、6社水泥路，全长2公里，宽4米；2.解决378人出行难问题。","吸纳脱贫户1人务工，增加脱贫人口年人均增收500元。"]
[16,"基础设施","阳平村4社路边沟建设项目","新建","阳平村4社","2026-05-01","2026-10-01","山河街道","全长1公里，双侧边沟。",59,59,{"$nulls":4},"受益50户110人。","1.修建长1公里，双侧边沟；2.解决农户110人排水问题。","吸纳脱贫户2人务工，增加贫困人口年人均增收500元。"]
[17,"基础设施","双营乡大营村大康屯路边沟建设项目","新建","大营村6社、7社、8社","2026-05-01","2026-10-01","双营乡","新建石砌路边沟1200米。",96,null,null,96,null,null,"受益脱贫户34户64人。","1.新建1200米路边沟。2.解决脱贫人口及农户出行难问题，改善农村居住环境和生产生活条件，促进乡村振兴。","吸纳脱贫人口2人务工，2.带动普通劳动力就近就业。"]
["合计",{"$nulls":8},{"$f":"SUM(J6:J22)","v":2425},{"$f":"SUM(K6:K22)","v":1319},{"$f":"SUM(L6:L22)","v":810},{"$f":"SUM(M6:M22)","v":296}]